## Sheet1
Item | Details | Cost (Person Weeks) | Comments
Tabs | Variations: Section, Application, Navigation, In-page Navigation | 8
Page Title |  | 2
Action Sets | Variations: Simple Page Menu, Dropdown Page Menu, Cluster+List, Modal | 6
Clusters | Variations: Standard, Nested | 2
Lists | Variations: Standard, Paginated, Scrollable, Expandable, Multi Select, Nested | 10
Modals |  | 2 | Modals are known for being very complex and "costly". That is more related to the behaviour of them and associated JavaScript. The styling is relatively straight forward.
Handcrafted Modals |  | 4 | We have a number of modal dialogs that are written "by hand" instead of being generated from UIM or inheriting from a base widget. Maintenance nightmare whenever we have to change modals. This has to be fixed.
Application Banner |  | 3
Shortcut and Smart Panels |  | 2
Form Widgets | Text Input, Text Area, Date picker, Frequeny picker, checkbox, radio button, Standard select, Multi select | 6
General Look + Feel | Setting base fonts, colors etc. | 2
Strip legacy CSS and Dojo customizations |  | 2
CSS + HTML Standards, guildelines (NFRs, rtl, a11y, etc) |  | 2
CSS Preprocessor |  | 2
Dojo customization strategy |  | 2
Images vs SVG icons |  | 2
All of above has to pave the way for getting rid of iframes |  | 2
renderers vs js widgets aka server vs browser html generation |  | 2
Component library |  | 2
Testing Framework |  | 2
Dojo version? Move to Dojo 2? Future of Dojo? |  | 2
Pods |  | ? | This is owned by CEF Widgets
Context Panel Rendering Infrastructure | Infrastructure provided by CEF Widgets for building context panels | ? | This is owned by CEF Widgets
Context Panels |  | 2 per instance | This is owned by individual application teams.
Summary Views | Variation of "Context Panels" used in expandable lists | 2 per instance | This is owned by individual application teams.